Still Becoming Launch Activation Runbook

Updated 2026-06-09 | Practical launch actions for Kindle, paperback, website, email, social, ads, and app gates.

OPERATING RULE Do not start paid book ads until the Amazon listing URL is live and the website book CTA has been updated. Until then, use organic posts and Starter Kit/list-building CTAs.

# Current Status

Kindle eBook submitted to KDP review on 2026-06-09; KDP says review can take up to 72 hours.

Paperback interior PDF is upload-ready; paperback setup waits on GetCovers full-wrap cover, paperback ISBN entry, KDP print preview, and physical proof.

Website is live with tools, Starter Kit, daily/weekly signup, consulting/speaking forms, Kit routing, Gmail notification, and Google Sheets lead repository.

App Store package was uploaded/accepted for processing; TestFlight/device UAT remains the open gate before App Review submission.

# Activation Timeline

| Trigger | Action | Owner | Status |
| --- | --- | --- | --- |
| Now | Keep website, tools, Starter Kit, consulting/speaking, and newsletter paths live. | Codex | Ready |
| Kindle listing live | Capture Amazon URL, update website book CTA, update email/social copy placeholders. | Codex | Waiting on KDP |
| Kindle listing live | Send Launch Email 1 and publish Day 15 launch post. | John/Codex | Needs approval/send |
| 24-48 hours after Kindle live | Post tool walkthrough and sample chapter CTA; start small lead-magnet ad test only if link paths are clean. | John/Codex | Staged |
| GetCovers final wrap received | Upload paperback interior/cover, enter ISBN/imprint, run KDP print preview. | John/Codex | Waiting on vendor |
| Paperback preview passed | Order physical proof. | John/Codex | Waiting on preview |
| Proof approved | Announce paperback availability and consider Amazon Ads. | John/Codex | Waiting on proof |
| TestFlight available | Run device UAT and submit App Review only after John approval. | John/Codex | Waiting on ASC |

# Email Sequence

| Email | Timing | Subject | CTA | Gate |
| --- | --- | --- | --- | --- |
| 1 | Kindle live day | You are not finished | Buy Kindle / get Starter Kit | Needs Amazon URL |
| 2 | +1 day | What carries you through transition | Foundation Inventory | Ready |
| 3 | +3 days | Stabilize before you reinvent | Use the scorecard | Ready |
| 4 | +5 days | Ownership is the door back | Use the Ownership Ladder | Ready |
| 5 | +7 days | The three questions reinvention asks | Use the Reinvention Intersection | Ready |
| 6 | +10 days | AI is a strategic partner | Use the AI ladder | Ready |
| 7 | +14 days | The work after the book | Book / consulting / speaking | Needs live links |

# Organic Content Plan

| Day | Theme | Primary CTA |
| --- | --- | --- |
| 1 | Kindle launch / You are not finished | Amazon Kindle + Starter Kit |
| 2 | Foundation Inventory | Starter Kit |
| 3 | Compliance is not commitment | Tools |
| 4 | AI as strategic partner | AI ladder |
| 5 | Stabilize first | Scorecard |
| 6 | Ownership ladder | Tools |
| 7 | Title is not identity | Starter Kit |
| 8 | Three rings / reinvention intersection | Tools |
| 9 | Grief is not an event | Newsletter |
| 10 | Speaking/workshop positioning | Speaking inquiry |
| 11 | Tool walkthrough video | Tools |
| 12 | Sample chapter | Starter Kit |
| 13 | Reader/reviewer feedback ask | Book link |
| 14 | Launch recap / next chapter | Website |

# $500 Spend Guardrails

| Channel | Cap | Start Condition | Stop Condition |
| --- | --- | --- | --- |
| Meta lead magnet test | $150 | Starter Kit and Kit delivery verified | Pause if cost per subscriber is above $6 after $60 spend |
| LinkedIn boost | $75 | An organic post shows above-average engagement | Pause if click-through is below 0.8% after $40 spend |
| Amazon Ads | $100 | Amazon listing is live and detail page looks clean | Pause if no sales after $50 spend or CPC is materially above category economics |
| Creative/tool screenshots | $75 | Use only if needed for clean ad or social visuals | Spend only on reusable templates/assets |
| Reserve | $100 | Hold for the channel that shows traction | Do not spend until one channel has evidence |

APPROVAL GATES John approves the first launch email before send, any paid spend before activation, the final paperback proof before paperback public launch, and TestFlight/App Review submission after device UAT.

# Immediate Next Actions

Wait for KDP Kindle review result and live Amazon URL.

Wait for GetCovers final paperback wrap.

Stage first launch email/social post with live-link placeholders.

Update website CTA and UAT script when the Amazon URL exists.

Keep tracking files current so launch decisions are visible without hunting through project notes.