Still Becoming Updated Task List

Printable execution task list | Updated 2026-06-09 | Internal controllable completion target: 2026-06-11

CURRENT FOCUS 10 open tasks remain. 8 are marked critical path. Internal target: complete all controllable work by 2026-06-11. John's active gates are limited to 8 items: final cover/proof approvals, paperback ISBN/account approvals, TestFlight/App Review approval, and launch spend/copy approval.

# Critical Path Task List

| ID | Stream | Task | Description | Owner | Due | Status | Critical | John Action | Next Step |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-043 | Publishing | Finalize cover revision package | Revised wrap and eBook images received 2026-06-01; design direction approved; final 226-page KDP wrap/page-count message sent to GetCovers 2026-06-08; GetCovers confirmed they are preparing final paperback files using approved design and KDP specs; waiting on final upload-ready cover files and flattened PSD source with editable text layer. | John/Codex/GetCovers | 2026-06-07 | In Progress | Yes | Approve final files/proof | Confirm final upload-ready cover files |
| SB-052 | Publishing | Stage KDP Kindle and paperback preview | Critical path. Kindle eBook submitted to KDP on 2026-06-09 and is In review; KDP Previewer passed with 0 spelling/image issues. Settings locked: $6.99 USD, 70% royalty, worldwide territories, no KDP Select, no DRM, imprint Still Becoming Tools Press, and no eBook ISBN. Paperback interior PDF is upload-ready; paperback staging waits on final GetCovers full-wrap cover and paperback ISBN entry. | Codex/John | 2026-06-11 | In Progress | Yes | Paperback preview/proof approval after final cover and ISBN entry | Kindle is submitted/in review; stage paperback when final cover and ISBN are ready |
| SB-053 | Publishing | Order/review KDP proof copy | Critical path for paperback. Review cover color, spine, page order, visuals, chapter openings, worksheets, and page breaks before approving paperback launch. | John/Codex | 2026-06-12 | Not Started | Yes | Approve final files/proof | Order/review physical proof |
| SB-054 | Publishing | Stage Apple Books eBook upload | Upload only after EPUB QA is stable; metadata must avoid Amazon/KDP-specific language and match cover/manuscript exactly. | Codex/John | 2026-06-12 | Not Started | Yes | Approval or account access if requested | Upload only after EPUB QA is stable; metadata must avoid Amazon/KDP-specific language and match |
| SB-055 | Publishing | Stage IngramSpark wide print upload | Add after KDP proof approval and final print files are stable; KDP Expanded Distribution must remain off if this route is used. | Codex/John | 2026-06-14 | Not Started | Yes | Approval or account access if requested | Add after KDP proof approval and final print files are stable; KDP Expanded Distribution must r |
| SB-057 | QA | Execute full website/PWA UAT pass | Critical path. Expanded production website/PWA UAT retest passed 9/9 on 2026-06-08. Post-deploy production regression retest passed 4/4 on 2026-06-09 after React dependency alignment and future Amazon CTA hook deploy. PWA offline fallback passed on 2026-06-09. Kit live delivery QA passed under SB-056 on 2026-06-09. Remaining true gate: set NEXT_PUBLIC_BOOK_RETAILER_URL in Vercel after Amazon listing URL is live and retest book order CTA. | Codex | 2026-06-10 | In Progress | Yes | None unless escalated | Execute UAT scripts and retest defects |
| SB-058 | Marketing | Load and approve launch email/social schedule | Launch Activation Runbook created 2026-06-09 with Kindle-live triggers, email schedule, organic content plan, book-link placeholders, and approval gates. Existing 7-email Kit copy and 21-day social/video copy are staged. Remaining gates: live Amazon URL, John approval before first launch send/post, and any account-side loading that requires manual authorization. | Codex/John | 2026-06-11 | In Progress | Yes | Approve launch copy/spend | Load launch sequence/calendar |
| SB-061 | iOS | Upload iOS build and complete TestFlight/App Review gate | Native Xcode archive/export/upload completed 2026-06-08. App Store Connect accepted the package and marked it processing. Remaining gate: TestFlight availability/device UAT, then Add for Review only after John approval. | John/Codex | 2026-06-11 | In Progress | Yes | Install/check TestFlight build; approve App Review only after UAT passes | Wait for App Store processing, then run TestFlight/device UAT |

# All Open / Active Tasks

| ID | Stream | Task | Description | Owner | Due | Status | Critical | John Action | Next Step |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-043 | Publishing | Finalize cover revision package | Revised wrap and eBook images received 2026-06-01; design direction approved; final 226-page KDP wrap/page-count message sent to GetCovers 2026-06-08; GetCovers confirmed they are preparing final paperback files using approved design and KDP specs; waiting on final upload-ready cover files and flattened PSD source with editable text layer. | John/Codex/GetCovers | 2026-06-07 | In Progress | Yes | Approve final files/proof | Confirm final upload-ready cover files |
| SB-052 | Publishing | Stage KDP Kindle and paperback preview | Critical path. Kindle eBook submitted to KDP on 2026-06-09 and is In review; KDP Previewer passed with 0 spelling/image issues. Settings locked: $6.99 USD, 70% royalty, worldwide territories, no KDP Select, no DRM, imprint Still Becoming Tools Press, and no eBook ISBN. Paperback interior PDF is upload-ready; paperback staging waits on final GetCovers full-wrap cover and paperback ISBN entry. | Codex/John | 2026-06-11 | In Progress | Yes | Paperback preview/proof approval after final cover and ISBN entry | Kindle is submitted/in review; stage paperback when final cover and ISBN are ready |
| SB-053 | Publishing | Order/review KDP proof copy | Critical path for paperback. Review cover color, spine, page order, visuals, chapter openings, worksheets, and page breaks before approving paperback launch. | John/Codex | 2026-06-12 | Not Started | Yes | Approve final files/proof | Order/review physical proof |
| SB-054 | Publishing | Stage Apple Books eBook upload | Upload only after EPUB QA is stable; metadata must avoid Amazon/KDP-specific language and match cover/manuscript exactly. | Codex/John | 2026-06-12 | Not Started | Yes | Approval or account access if requested | Upload only after EPUB QA is stable; metadata must avoid Amazon/KDP-specific language and match |
| SB-055 | Publishing | Stage IngramSpark wide print upload | Add after KDP proof approval and final print files are stable; KDP Expanded Distribution must remain off if this route is used. | Codex/John | 2026-06-14 | Not Started | Yes | Approval or account access if requested | Add after KDP proof approval and final print files are stable; KDP Expanded Distribution must r |
| SB-057 | QA | Execute full website/PWA UAT pass | Critical path. Expanded production website/PWA UAT retest passed 9/9 on 2026-06-08. Post-deploy production regression retest passed 4/4 on 2026-06-09 after React dependency alignment and future Amazon CTA hook deploy. PWA offline fallback passed on 2026-06-09. Kit live delivery QA passed under SB-056 on 2026-06-09. Remaining true gate: set NEXT_PUBLIC_BOOK_RETAILER_URL in Vercel after Amazon listing URL is live and retest book order CTA. | Codex | 2026-06-10 | In Progress | Yes | None unless escalated | Execute UAT scripts and retest defects |
| SB-058 | Marketing | Load and approve launch email/social schedule | Launch Activation Runbook created 2026-06-09 with Kindle-live triggers, email schedule, organic content plan, book-link placeholders, and approval gates. Existing 7-email Kit copy and 21-day social/video copy are staged. Remaining gates: live Amazon URL, John approval before first launch send/post, and any account-side loading that requires manual authorization. | Codex/John | 2026-06-11 | In Progress | Yes | Approve launch copy/spend | Load launch sequence/calendar |
| SB-061 | iOS | Upload iOS build and complete TestFlight/App Review gate | Native Xcode archive/export/upload completed 2026-06-08. App Store Connect accepted the package and marked it processing. Remaining gate: TestFlight availability/device UAT, then Add for Review only after John approval. | John/Codex | 2026-06-11 | In Progress | Yes | Install/check TestFlight build; approve App Review only after UAT passes | Wait for App Store processing, then run TestFlight/device UAT |
| SB-062 | Platform | Post-launch dependency audit and framework upgrade plan | Not a launch blocker. npm audit --omit=dev reports 12 moderate issues, but available fixes require breaking/preview upgrades to Next or Expo. Leave stable launch stack in place; evaluate safe upgrades after Kindle/paperback/iOS launch gates are complete. | Codex | 2026-06-30 | Not Started | No | None unless escalated | Not a launch blocker. npm audit --omit=dev reports 12 moderate issues, but available fixes requ |
| SB-063 | Publishing | Plan and stage KDP hardcover edition | Non-critical-path extension. KDP hardcover is case laminate only, no dust jacket; use 6 x 9 if accepted, black-and-white interior on white paper, separate hardcover ISBN, and a separate KDP hardcover full-wrap cover file from GetCovers. Do not delay Kindle, paperback proof, Apple Books, or launch activation. | Codex/John | 2026-06-14 | Not Started | No | Approval or account access if requested | Non-critical-path extension. KDP hardcover is case laminate only, no dust jacket; use 6 x 9 if |

# Recently Completed / Locked Decisions

| ID | Stream | Task | Description | Owner | Due | Status | Critical | John Action | Next Step |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SB-045 | Website | Promote legal pages to production | John approved production promotion; Vercel production deploy completed; homepage, /privacy, /terms, and /disclaimer verified 200 OK on stillbecomingtools.com | Codex/John | 2026-06-03 | Done | No | None | Complete |
| SB-046 | Website | Complete consulting/speaking inquiry routing and notifications | Production code deployed 2026-06-03. Inquiry submissions save to Kit with custom fields even without a dedicated Kit-hosted form. Gmail SMTP notification support deployed. Google App Password added to Vercel. Live inquiry test returned success and John confirmed receipt of Gmail notification. | Codex | 2026-06-03 | Done | No | None | Complete |
| SB-047 | Website/Data | Add required Google Sheets lead and inquiry repository | Zapier Catch Hook + security filter + Google Sheets row action published. Production Vercel env vars added. Live consulting and speaking inquiry tests returned sheetStatus: sent; rows verified in Inquiries; John confirmed Gmail notification receipt. | Codex/John | 2026-06-04 | Done | No | None | Complete |
| SB-048 | Publishing | Lock print and distribution route | Approved path: KDP direct for Amazon paperback/Kindle, Apple Books after EPUB QA, IngramSpark for wide print after KDP proof approval, owned Bowker paperback ISBN, imprint Still Becoming Tools Press, and no KDP Expanded Distribution. | Codex/John | 2026-06-04 | Done | No | None | Complete |
| SB-051 | Publishing | Decide owned ISBN and imprint details | Locked decision: buy/use 1 owned Bowker paperback ISBN, imprint Still Becoming Tools Press, no Kindle/Apple eBook ISBN for initial launch, KDP Expanded Distribution off, use same paperback ISBN for IngramSpark after KDP proof approval. | John/Codex | 2026-06-06 | Done | Yes | None | Complete |

# John Approval Gates

| Gate | Decision | Owner | Needed By | Type | Decision / action needed |
| --- | --- | --- | --- | --- | --- |
| JG-013 | Editor changes | John/Codex | 2026-06-06 | Critical | Review only held meaning/voice/legal items after Codex first pass. |
| JG-014 | Owned ISBN / imprint | John/Codex | 2026-06-06 | Done | Locked: owned Bowker paperback ISBN; imprint Still Becoming Tools Press; no initial eBook ISBN. |
| JG-015 | Final cover / spine wrap | John/Codex/GetCovers | 2026-06-11 | Critical | Approve final eBook cover and paperback wrap after final page count. |
| JG-007 | KDP preview approval | John | 2026-06-12 | Critical | Kindle preview is complete and eBook is submitted; paperback preview/proof approval remains after final cover. |
| JG-016 | Ad activation | John/Codex | 2026-06-11 | Launch | Approve spend guardrails and first creative set. |
| JG-017 | iOS/TestFlight scope | John/Codex | 2026-06-08 | Done | Decision locked: proceed with MVP/TestFlight now; defer saved library, account sync, and PDF export. |